## Sheet1
TO DO LIST
Task | Priority | Responsible | Notes | Status
Electrical
Install Nest thermostats throughout building | 1 | Chris | 83.33% | All 6 installed. 1 is being finicky
Finish electric project in sound closet | 2 | Chris | Work Day 12-12-2020
Pull old wires from the attic | 3 | Team | Work Day 12-12-2020
Install switch plate in back of sanctuary | 4 | Chris | Work Day 12-12-2020
Install track lights up on the platform | 5 | Chris/Ron | Jan 2021 | Needs scaffolding
Install fans in the sanctuary | 6 | Chris/Ron | Jan 2021 | Needs scaffolding
Install smoke detectors | 7 | Chris/Ron | Jan 2021 | Needs scaffolding
Fix light in exterior sign | 8 | TBD | TBD
Outside
Install Snow marker | 1 | Team | Work Day 12-12-2020
Install Handicap Signs | 2 | Team | Work Day 12-12-2020
Repaint stripes in the parking lot | 3 | Team | Spring 2021
Paint new stripes in the parking lot | 4 | Team | Spring 2021
Basement
Finish closet | 1 | Andrew B / Bryan B | 0%
Finish Drywall Spackling | 2 | Andrew B / Bryan B | 33%
Install trim downstairs | 3 | Team | 0%
Paint ceilings downstairs | 4 | Team | 0%
Paint walls downstairs | 5 | Team | 0%
Strip wax from downstairs floor | 6 | Ben Hershey | 0%
Install Flooring | 7 | TBD | 0%
Install Sink Base | 8 | Chris Groft | 0%
Install Countertop/Sink | 9 | Chris Groft | 0%
Final Sink Plumbing | 10 | Chris Groft | 0%
General Maintenance
Throw out dead plants in small lobby | 1 | Team | Work Day 12-12-2020
Caulk floor trim in lobby | 2 | Ben | Work Day 12-12-2020
Clean windows in the back stairwell | 3 | Team | Work Day 12-12-2020
Wash exterior of lobby windows (If weather permits) | 4 |  | Work Day 12-12-2020
Finish spackling | 5
Drywall Switch area |  |  | Temporary
Clean up sound closet |  | Sound Team | Work Day 12-12-2020
Cleanup deacon closet |  |  | Work Day 12-12-2020